## Sheet1
New Air Quality Prediction Dashboard (with Deep Learning) v1
Purpose | Display air pollutant concentration prediction from deep learning-based model
Phase | Sub-phase | Milestone | Assigned to | Progress | Timeline
[5 empty] | Jan | [15 empty] | Feb | [27 empty] | Mar
[5 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Initial |  | Analyse previous dashboard |  | 100% | bar: Jan 16 to Jan 23
|  | Reference existing websites |  | 100% | bar: Jan 16 to Jan 24
|  | Sketch skeletal layout |  | 100% | bar: Jan 25 to Feb 1
Development | Public deployment | Display map |  | 64.44%
|  | Utilise open-source map |  | 100% | bar: Jan 25 to Feb 6
|  | Display markers for AQ stations (demonstrative) |  | 100% | bar: Feb 6 to Feb 8
|  | Display markers for real AQ stations |  | 100% | bar: Feb 7 to Feb 12
|  | Display popup with air pollutant info |  | 100% | bar: Feb 6 to Feb 14
|  | Graph timeseries of predicted air pollutants |  | 100% | bar: Feb 13 to Feb 21
|  | Overlay contour map (layers) of air pollutants |  | 10% | bar: Feb 20 to Mar 7
|  | Play animations of air pollutant layers |  | 10% | bar: Feb 27 to Mar 14
|  | Supplementary map improvement |  | 20% | bar: Mar 15 to Mar 21
|  | Review |  | 40% | bar: Jan 25; Feb 1; Feb 8; Feb 15; Feb 22; Mar 1; Mar 8; Mar 15; Mar 22; Mar 29
|  | Users' interaction functionalities |  | 66.67%
|  | Choose prediction model |  | 100% | bar: Feb 1 to Feb 14
|  | Choose region |  | 50% | bar: Feb 15 to Feb 21
|  | Choose time |  | 50% | bar: Feb 15 to Feb 21
|  | Polish UI design |  | 20% | bar: Feb 22 to Mar 1
|  | Server deployment |  | 0%
|  | Pre-deploy test |  | 0% | bar: Mar 5 to Mar 11
|  | Post-deploy test |  | 0% | bar: Mar 12 to Mar 19
| For internal use | Modification of the public version |  | 0% | bar: Mar 8 to Mar 14
|  | Inclusion of more statistical data |  | 0% | bar: Mar 8 to Mar 21
Handover |  | Users' guide |  | 0%
|  | Code and functionality documentation |  | 0% | bar: Mar 22 to Mar 29
|  | Review |  | 0% | bar: Mar 29 to Mar 31
|  | Professional Involvement (future) |  | 0%