## Sheet1
New Air Quality Prediction Dashboard (with Deep Learning) v1
Phase | Sub-phase | Milestone | Progress | Timeline
|  |  |  | Jan | [15 empty] | Feb | [27 empty] | Mar
|  |  |  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Initial |  | Analyse previous dashboard | 100% | bar: Jan 16 to Jan 23
|  | Reference existing websites | 100% | bar: Jan 16 to Jan 24
|  | Sketch skeletal layout | 100% | bar: Jan 25 to Feb 1
Development | Public deployment | Display map | 27.78%
|  | Utilise open-source map | 100% | bar: Jan 25 to Feb 6
|  | Display markers for AQ stations (demonstrative) | 100% | bar: Feb 6 to Feb 8
|  | Display markers for real AQ stations | 20% | bar: Feb 7 to Feb 12
|  | Display popup with air pollutant info | 0% | bar: Feb 6 to Feb 14
|  | Graph timeseries of predicted air pollutants | 0% | bar: Feb 13 to Feb 21
|  | Overlay contour map (layers) of air pollutants | 0% | bar: Feb 20 to Mar 7
|  | Play animations of air pollutant layers | 0% | bar: Feb 27 to Mar 14
|  | Supplementary map improvement | 0% | bar: Mar 15 to Mar 21
|  | Review | 30% | bar: Jan 25; Feb 1; Feb 8; Feb 15; Feb 22; Mar 1; Mar 8; Mar 15; Mar 22; Mar 29
|  | Users' interaction functionalities | 16.67%
|  | Choose prediction model | 50% | bar: Feb 1 to Feb 14
|  | Choose region | 0% | bar: Feb 15 to Feb 21
|  | Choose time | 0% | bar: Feb 15 to Feb 21
|  | Polish UI design | 0% | bar: Feb 22 to Mar 1
|  | Server deployment | 0%
|  | Pre-deploy test | 0% | bar: Mar 15 to Mar 21
|  | Post-deploy test | 0% | bar: Mar 22 to Mar 29
| For internal use | Modification of the public version | 0% | bar: Mar 8 to Mar 14
|  | Inclusion of more statistical data | 0% | bar: Mar 8 to Mar 21
Handover |  | Users' guide | 0%
|  | Code and functionality documentation | 0% | bar: Mar 22 to Mar 29
|  | Review | 0% | bar: Mar 29 to Mar 31
|  | Professional Involvement (future) | 0%